GEMINI CAPITAL TRADING PLATFORM

Architecture Redesign

Project Plan

Version 1.0  |  April 1, 2026

Duration: 7 Weeks  |  4 Phases  |  30 Tasks

Classification: CONFIDENTIAL

# 1. Project Overview

This project plan details the phased implementation of the Gemini Capital platform architecture redesign. All work is performed on a live trading system managing real capital — every change must be backward-compatible during transition with instant rollback capability.

| Parameter | Value |
| --- | --- |
| Timeline | April 7 - May 25, 2026 (7 weeks) |
| Phases | 4: Foundation (Wk 1-2), Core Migration (Wk 3-4), Integration (Wk 5-6), Consolidation (Wk 7) |
| Execution Model | Claude + Dale — Claude builds and deploys, Dale reviews and approves go/no-go gates |
| Environment | DigitalOcean VPS (178.62.225.235), Python 3.x, SQLite, Flask, cron-based scheduling |
| Constraint | Zero trading downtime during migration — dual-write/dual-read with instant rollback at every phase gate |
| Success Metric | Zero false lockouts, 100% resolution capture, single config source, <30s pre-deploy validation |

# 2. Phase 1 — Foundation (Week 1-2: April 7-20)

Objective: Establish the infrastructure that all other changes depend on — database schema, decision logging, centralized config, and test harness. No trading logic changes. No risk to live operations.

| # | Task | Duration | Depends | Deliverable | Acceptance |
| --- | --- | --- | --- | --- | --- |
| 1.1 | Initialize git repo on VPS, import current codebase, remove 50 backup files + 14 fix scripts | 2 hours | None | Clean git repo with initial commit, .gitignore for state/logs | git log shows history, no backups in tree |
| 1.2 | Create polybot.db schema — events, positions, balances, decisions, config_history tables | 3 hours | 1.1 | polybot.db with empty tables + migration script | Schema matches implementation plan spec |
| 1.3 | Build config.json from scattered constants + config_loader.py with fallback | 2 hours | 1.1 | config.json + config_loader.py | All 6+ config sources unified, fallback works if config.json deleted |
| 1.4 | Build decision logger — write to decisions table on every trade/size/reject event | 3 hours | 1.2 | decision_logger.py + integration with sprint_trader and grinder | Decisions appear in DB within 15 min of cron cycle |
| 1.5 | Migrate existing decisions.jsonl (134 entries) into decisions table | 1 hour | 1.2, 1.4 | Migration script + validation query | 134 rows in decisions table matching jsonl content |
| 1.6 | Build test harness — smoke tests (all imports), unit tests (Kelly sizing), pre_deploy.sh | 4 hours | 1.1 | tests/ directory + pre_deploy.sh | pre_deploy.sh runs in <30s, catches import errors |
| 1.7 | Build event emitter — emit() function that writes to events table | 2 hours | 1.2 | events.py with emit(), query_latest(), replay() functions | Events persisted and queryable |
| 1.8 | GATE: Phase 1 validation — all tests pass, decision logger capturing data, config.json active | 2 hours | 1.1-1.7 | Validation report: test results + decision count + config diff | Dale approves go/no-go for Phase 2 |

Phase 1 Total: ~19 hours across 2 sessions. No changes to trading logic. No risk to live operations.

Rollback: Delete polybot.db and config.json. System reverts to JSON-only state. Zero impact.

# 3. Phase 2 — Core Migration (Week 3-4: April 21 - May 4)

Objective: Migrate state management from JSON files to SQLite. Dual-write mode — both JSON and SQLite updated simultaneously. Reads gradually shifted from JSON to SQLite after validation.

| # | Task | Duration | Depends | Deliverable | Acceptance |
| --- | --- | --- | --- | --- | --- |
| 2.1 | Dual-write: reconcile.py writes portfolio snapshots to both portfolio.json AND balances table | 3 hours | 1.7 | Modified reconcile.py + dual_write_adapter.py | Both JSON and DB updated every 5 min, values match |
| 2.2 | Dual-write: risk_manager.py writes equity/HWM to both reserve.json AND balances table | 3 hours | 1.7, 2.1 | Modified risk_manager.py | HWM, trading_balance in DB match JSON |
| 2.3 | Build resolution pipeline — reconcile.py emits resolution_detected events when positions close | 4 hours | 1.7, 2.1 | resolution_pipeline.py + events integration | Resolutions captured automatically (test with next batch of market resolutions) |
| 2.4 | Migrate is_trading_allowed() to read from balances table instead of reserve.json | 2 hours | 2.2 | Modified risk_manager.py with DB-first reads | Lockout check uses DB equity. JSON fallback if DB unavailable. |
| 2.5 | Build edge estimator v2 — derives win rate and payoff ratio from resolved positions in DB | 3 hours | 2.3 | edge_estimator_v2.py reading from positions table | Edge estimates match or improve on current inference-based method |
| 2.6 | Validation week: monitor dual-write consistency for 7 days. Compare JSON vs DB on every cycle. | 7 days passive | 2.1-2.4 | Daily consistency report (automated) | Zero divergence for 7 consecutive days |
| 2.7 | GATE: Phase 2 validation — dual-write stable, resolution pipeline capturing, edge v2 validated | 2 hours | 2.6 | Validation report: consistency stats, resolution count, edge comparison | Dale approves cutover from JSON to DB reads |

Phase 2 Total: ~17 hours of active work + 7 days of passive validation.

Rollback: Set DB_READ_ENABLED=false in config.json. All reads revert to JSON files instantly. Dual-write continues.

Critical milestone: After Phase 2, the lockout loop is structurally eliminated — equity checks hit the same database that records trades.

# 4. Phase 3 — Integration (Week 5-6: May 5-18)

Objective: Build the plugin architecture, consolidate the dashboard, and wire everything together. Trading logic changes for the first time — Kelly Engine moves from shadow to live mode via the plugin system.

| # | Task | Duration | Depends | Deliverable | Acceptance |
| --- | --- | --- | --- | --- | --- |
| 3.1 | Build pipeline.py — trading pipeline with hook points (pre_scan, pre_size, pre_trade, post_trade, on_resolution, on_error) | 4 hours | 2.7 | pipeline.py with hook registry | Hooks fire in correct order, existing trading behavior unchanged |
| 3.2 | Wrap sprint_trader.py in pipeline adapter — existing code runs inside pipeline, hooks fire around it | 3 hours | 3.1 | sprint_trader_adapter.py | Sprint trader produces identical trades via adapter |
| 3.3 | Wrap grinder.py in pipeline adapter | 2 hours | 3.1 | grinder_adapter.py | Grinder produces identical trades via adapter |
| 3.4 | Register Kelly Engine as pre_size plugin — remove inline try/except from grinder and sprint_trader | 3 hours | 3.1, 3.2, 3.3 | kelly_plugin.py (replaces inline patches) | Kelly sizing logged via plugin, no inline code in trading scripts |
| 3.5 | Register decision logger as pre_trade plugin | 1 hour | 3.1, 1.4 | decision_logger registered as plugin | All decisions captured via plugin hook |
| 3.6 | Build unified multi-tenant dashboard on port 9091 | 6 hours | 2.7 | dashboard_v2/ — single Flask app, entity via URL path, DB-backed | All 15 entities render correctly on single service |
| 3.7 | Kelly Engine live mode transition (if weekly report says GO LIVE) | 2 hours | 3.4 | config.json: features.kelly_live_mode = true | Kelly sizes actual trades, comparison logged |
| 3.8 | GATE: Phase 3 validation — pipeline stable, plugins firing, dashboard v2 operational | 2 hours | 3.1-3.6 | Validation report: plugin execution logs, dashboard screenshots, trade comparison | Dale approves consolidation |

Phase 3 Total: ~23 hours. First phase with trading logic changes — highest risk phase.

Rollback: Revert cron entries to call sprint_trader.py and grinder.py directly (bypass pipeline adapter). Dashboard v1 still running on original ports.

# 5. Phase 4 — Consolidation (Week 7: May 19-25)

Objective: Remove legacy components, cut over to new dashboard, finalize cleanup. System reaches target architecture.

| # | Task | Duration | Depends | Deliverable | Acceptance |
| --- | --- | --- | --- | --- | --- |
| 4.1 | Stop JSON dual-writes — SQLite is sole source of truth | 1 hour | 3.8 | Remove dual_write_adapter.py, archive JSON state files | System runs on DB-only for 48h without issues |
| 4.2 | Cut over dashboard: nginx rewrite from old ports to dashboard_v2 on 9091 | 2 hours | 3.6, 3.8 | nginx config updated, old dashboard services disabled | All entity URLs resolve to new dashboard |
| 4.3 | Decommission old dashboard services — remove 15 systemd units | 1 hour | 4.2 | systemd units removed, ports freed | Only 1 dashboard process running |
| 4.4 | File cleanup — archive dead code, organize into package structure | 3 hours | 4.1 | polybot/ package with core/, strategies/, plugins/, etc. | Package structure matches implementation plan |
| 4.5 | Update cron jobs — reduce from 29 to ~15 (consolidate overlapping schedules) | 2 hours | 4.4 | Cleaned crontab, documented schedule | All critical functions run, no duplicates |
| 4.6 | Update monitoring — health check and watchdog adapted for new architecture | 2 hours | 4.1, 4.4 | Updated email_report.py --health-check and watchdog.py | Health checks pass against new architecture |
| 4.7 | Final documentation — update system_status report with new architecture | 2 hours | 4.1-4.6 | Updated system_status_2026-05-25.md | Documentation matches deployed system |
| 4.8 | GATE: Project complete — full validation against success criteria | 3 hours | 4.1-4.7 | Final validation report with all 8 success metrics | All success criteria met, Dale signs off |

Phase 4 Total: ~16 hours. Lowest risk — removing legacy components after new system is proven.

# 6. Critical Path and Dependencies

The critical path runs through the database migration. If the dual-write validation in Phase 2 (task 2.6) reveals consistency issues, Phase 3 cannot begin. All other work items can proceed in parallel.

## 6.1 Dependency Chain (Critical Path)

1.2 (DB schema) -> 1.7 (event emitter) -> 2.1 (dual-write) -> 2.4 (DB-first reads) -> 2.6 (7-day validation) -> 3.1 (pipeline) -> 3.4 (Kelly plugin) -> 4.1 (JSON removal)

## 6.2 Parallel Tracks

- Track A (Database): 1.2 -> 1.7 -> 2.1 -> 2.2 -> 2.3 -> 2.4 -> 2.6 (critical path)

- Track B (Testing): 1.6 -> runs continuously, gates every deployment

- Track C (Config): 1.3 -> used by all subsequent tasks

- Track D (Observability): 1.4 -> 1.5 -> 3.5 (decision logger, parallel to DB work)

- Track E (Dashboard): 3.6 -> 4.2 -> 4.3 (independent after Phase 2 gate)

# 7. Effort Summary

| Phase | Active Hours | Calendar | Risk Level | Key Deliverable |
| --- | --- | --- | --- | --- |
| 1. Foundation | 19 hours | Week 1-2 | LOW — no trading changes | Database, config, tests, decision logger |
| 2. Core Migration | 17 hours + 7d passive | Week 3-4 | MEDIUM — dual-write mode | DB-first reads, resolution pipeline, edge v2 |
| 3. Integration | 23 hours | Week 5-6 | HIGH — trading logic changes | Pipeline, plugins, unified dashboard, Kelly live |
| 4. Consolidation | 16 hours | Week 7 | LOW — removing legacy | Cleanup, decommission, documentation |
| TOTAL | 75 hours | 7 weeks |  |  |

Estimated sessions: ~12-15 Cowork sessions at 5-6 hours each, spread across 7 weeks.

Constraint: Trading continues uninterrupted throughout. Every phase gate requires Dale approval before proceeding. Every phase has instant rollback.

# 8. Variance Capture Integration

The 5 identified variance captures (from the compounded growth strategy) map directly onto the new architecture. The redesign enables cleaner implementation of each.

| Variance | Current State | After Redesign | Enabled By | Phase |
| --- | --- | --- | --- | --- |
| V1 Kelly | Shadow mode, 134 decisions, inline patched into grinder/sprint | Plugin registered via pipeline, DB-backed decisions, clean go-live path | Plugin architecture (3.4) | Phase 3 — Kelly becomes a plugin |
| V2 Idle Cap | Not started. Needs margin calculator. | Plugin that hooks post_trade to track idle capital. Reads balances from DB. | Unified DB (2.1), Plugin arch (3.1) | Post Phase 3 — separate plugin |
| V3 Settlement | Blocked on Kalshi account. NLP parser not built. | Plugin that hooks pre_scan to evaluate settlement semantics. Cross-platform via events. | Plugin architecture (3.1), Events (1.7) | Post Phase 3 — needs Kalshi first |
| V4 RPC | Deferred until 50+ trades/day | Infrastructure improvement — RPC failover chain in config.json | Centralized config (1.3) | Phase 1 config + later implementation |
| V5 Observability | Partial — decisions.jsonl (134 entries), dashboards show Kelly panel | Fully satisfied by decisions table + event log. Decision logger IS V5. | Decision logger (1.4), Events (1.7) | Phase 1 — built as foundation |

Key insight: V5 (Agent Observability) is no longer a separate variance — it is the foundation layer (Phase 1) that enables everything else. V1 (Kelly) becomes a clean plugin in Phase 3. V2 and V3 register as additional plugins post-Phase 3 without any core code changes.

# 9. Phase Gates — Go/No-Go Criteria

| Gate | Go Criteria | No-Go Criteria | Decision Maker |
| --- | --- | --- | --- |
| Gate 1 | All tests pass. Decision logger capturing data. Config.json active with fallback. Git repo initialized. | Import errors in any module. Decision logger not writing. Config loader fallback broken. | Dale + Claude joint review |
| Gate 2 | 7 days of dual-write with zero divergence. Resolution pipeline capturing. Edge v2 estimates reasonable. | Any JSON/DB divergence. Resolution pipeline missing events. Edge estimates diverge >20% from current. | Dale approves DB cutover |
| Gate 3 | Pipeline adapter produces identical trades. Plugins fire correctly. Dashboard v2 renders all entities. | Any trade discrepancy between adapter and direct execution. Plugin errors. Dashboard rendering failures. | Dale approves consolidation |
| Gate 4 | All 8 success metrics met. System stable for 48h on new architecture. Documentation complete. | Any success metric not met. Stability issues in 48h burn-in. | Dale signs off on project |

End of Project Plan.